## Schedule A - Schedule of Prices
Appendix F - Schedule of Prices
Schedule A - Cost Breakdown
Submission by
(Full Legal Nme of Company or Individual
H.S.T. Number
(H.S.T Number of Company or Individual
Phase | Item Number | Item Name | Specification | Unit | Quantity | Unit Price | Cost
1 | 1.1 | Strip and stockpile topsoil (approx 0.15m depth) | OPSS.MUNI 206 | m2 | 4083 |  | 0
1 | 1.2 | Install geoxtextile (partially supplied by ONTC) | OPSS.MUNI 1860 | m2 | 4083 |  | 0
2 | 2.1 | 450mm dia. Culvert installation (ONTC supplied) | OPSS.MUNI 421 | m | 38 |  | 0
2 | 2.2 | 750mm dia. Culvert installation (ONTC supplied) | OPSS.MUNI 421 | m | 16 |  | 0
3 | 3.1 | Place and compact fill materials (Gran B1, compacted to 95%) | OPSS.MUNI 501, 1010 | tonnes | 2887 |  | 0
4 | 4.1 | Place and compact subbase materials (Gran B1, compacted to 95%) | OPSS.MUNI 501, 1010 | tonnes | 1939 |  | 0
4 | 4.2 | Place and compact base materials (Gran A, compacted to 95%) | OPSS.MUNI 501, 1010 | tonnes | 954 |  | 0
5 | 5.1 | Place 150mm topsoil along roadway slopes | OPSS.MUNI 206 | m3 | 236 |  | 0
5 | 5.2 | Ditch existing entrance | OPSS.MUNI 510 | m3 | 33 |  | 0
5 | 5.3 | Remove existing entrance culvert | OPSS.MUNI 510 | ea | 1 |  | 0
5 | 5.4 | Remove existing driveway | OPSS.MUNI 510 | m3 | 273 |  | 0
5 | 5.5 | Place 150mm topsoil on disturbed areas | OPSS.MUNI 510 | m3 | 102 |  | 0
Total (excluding HST) | [6 empty] | 0

## Sch. B - Pricing for Change Ord
SCHEDULE B - PRICING FOR CHANGE ORDERS / CHANGE DIRECTIVES:
Please quote overhead and profit percentage based on the following project cost ranges:
Project Costs | Overhead % | Profit %
$0 up to $9,999
$10,000 up to $49,999
$50,000 up to $99,999
$100,000 up to 149,999
$150,000 up to $200,000
$200,000 and higher
Please note that these project cost ranges apply to the aggregate price of all change orders and not on a per change order basis. Any OH&P applied shall be calculated against the subtotal of the applicable change order only. ONTC reserves the right to not accept the percentage values provided in the table above and any future change order markups will be reviewed and agreed upon by ONTC and contractor.
Please provide the hourly rate of pay for the following (add an additional page for any Positions not listed below):
Position | Hourly Rate
Project Manager
Estimator
Scheduler
Civil Engineering
Site Supervisor
Carpenter
Electrician
Mechanical Engineer
Mechanical HVAC Contractor Technician
Masonry/Concrete Labour
Concrete Truck Operator
Crane Operator
Welder
Roofer
General Labour

## Sched C - Sched of Prog. Pmts.
Schedule C - Schedule of Progress Payments
Please provide your schedule of progress payments below identifying all payment milestones, associated deliverables, and corresponding payment amounts or percentages.